## Slide 1
Research Process Flow
Discover-NOW
January 2021
Notes: Dusan

## Slide 2
Discover-NOW Process Flow for Real-World Evidence Research
* depending when the Application is received (Group meets monthly every 3rd Thursday at 9:30am, application to be submitted to Discover-NOW by 1st Monday of the month will be triaged and presented the same month); the decision of the DAG is given on the day and written confirmation of approval or refusal is provided the next working day). The PI is required to dial in to the meeting.
i. Note no data extractions are allowed prior to this approval being granted.
Identify and engage a NWL PI (Principal Investigator)
Agree scope of the project and research questions defined, funding
Client contract development/ vendor formalities
Generate application to NWL DAG
Client agreement with final proposal and client contract signed
NWL PI to complete application form and obtain Letter of Support from the Head of Department/R&D
Process Interaction
Client Interaction
NWL Data Access Group*
Feedback given to applicant & access details provided
No
Approved
Data access to data required
Research conducted and report provided to client
No
Research question received
Recruitment to a study
Retrospective research
What type of research is the project?
Feasibility
Complete all required fields in application form
No
All required fields completed?
Yes
Query executed
Access forms signed
User account created & access details provided
Researchers conduct projects
Yes
Client agreement with final proposal and client contract signed
Yes
Notes: RFP or research questions received
Identify and engage a NWL Principal Investigator - 1-4 weeks
Agree scope of the project with client and research questions – 1-4 weeks (1,2,3 can run concurrently with 6,7, however clients tend to delay 6,7 until 5)
NWL Investigator to complete application form and obtain Letter of Support from the Head of Department (mandatory before the application can be considered)
Generate draft and the final proposal – 2-4 weeks (final agreed research objectives, deliverables and costs)
Client agrees with the final proposal – 1 day – x weeks)
Vendor formalities and NV approval – 1-5 weeks
Contract with client – 1 day – 10+ weeks
NWL Data Access Sub-Group – up to 4 weeks, depending when the application is received (Group meets monthly every 3rd Thursday at 9:30am, application to be submitted to Discover by 2nd Thursday; the decision is given on the day). The PI needs to be either present or dial in to this meeting.
i. Note no data extractions are allowed prior to this approval being granted.
Kick-Off meeting – 1 day
Scoping – research questions, variables defined and analysis plan/ Output Data Tables, protocol development, agree final protocol and tables to populate
Data Extraction and Analysis – 2-6 weeks , perform data extraction, run quality control, populate shell tables
Data iteration 2 – 1-6 weeks
Data Iteration 3 – 1-6 weeks
Final Review of data – 1-3 week
Reporting -2-6 weeks

## Slide 3
Retrospective Analysis Stage – Typical simplified flow
Kick-off meeting
Scoping**
Data Extraction and Analysis ***
Data Analysis Iterations
Final Review of Data
Reporting
**research questions, variables defined and analysis plan/ Output Data Tables, protocol development, agree final protocol and tables to populate
*** perform data extraction, run quality control, populate shell tables
Entry dependent on completion and approval by NWL Data Access Group